OrchestrAI Team Knowledge Base

Change Request Workflow

Workflow standard for evaluating scope, date, and dependency changes affecting committed OrchestrAI roadmap items or release targets.

| Document ID VAL-PROD-002 | Department Product & Program Management | Owner PMO Governance Lead | Version 1.0 |
| --- | --- | --- | --- |
| Effective Date 2026-03-24 | Review Cycle Quarterly | Audience PMO, Product, Engineering Managers, Security, Operations | Classification Internal |

Purpose. Use this workflow when a committed initiative changes in scope, target date, dependency path, launch sequence, or staffing assumptions after the planning baseline has been approved.

When a formal change request is required

Launch date moves by more than five business days for a customer-facing release.

A dependency team adds work that changes critical-path timing or funding assumptions.

A scope change alters security posture, packaging, commercial commitments, or operational readiness requirements.

Workflow stages

| Stage | Required action | Accountable owner | Target timing |
| --- | --- | --- | --- |
| 1. Intake | Submit CR form in LaunchHub with change summary, reason, affected milestone, and requested decision date. | Requester | Same business day |
| 2. Impact review | Assess engineering effort, downstream risks, security effects, enablement impact, and customer-commitment exposure. | PMO + functional leads | 2 business days |
| 3. Decision forum | Review recommendation in change board or weekly portfolio review and approve, reject, or defer. | PMO governance chair | Next governance meeting |
| 4. Baseline update | Update roadmap board, release calendar, launch plan, risk register, and owner list. | PMO | Within 1 business day |
| 5. Communication | Notify impacted teams and account owners when customer dates, enablement, or service windows shift. | Product + PMO | Within 1 business day |

Decision criteria

Decision-makers should weigh customer and revenue commitments, implementation risk, operational readiness, security obligations, and whether the proposed change reduces or increases overall portfolio risk. Requests that only transfer hidden work into later milestones without reducing delivery risk should normally be rejected.

Required evidence package

Short change summary with reason code: defect, dependency, capacity, compliance, market need, or external partner change.

Impact statement covering customer commitments, support readiness, and risk if the request is denied.

Revised milestone plan with named owners for every downstream action.

Common retrieval phrases

Useful search cues include change request, scope change, target date shift, baseline update, dependency impact, portfolio review, and governance board approval.