ORCHESTRAI INTERNAL KNOWLEDGE BASE

# New Customer Onboarding Timeline

Document ID: VAL-CS-002   Department: Customer Success & Support   Confidentiality: Internal Use Only

| Owner | Manager, Implementation Success | Document type | Timeline brief |
| --- | --- | --- | --- |
| Effective date | 2026-02-10 | Review date | 2026-08-10 |

Purpose: Summarizes the standard onboarding timeline used for new OrchestrAI warehouse deployments. The timeline is intentionally concise and date-oriented so retrieval can answer questions about kickoff, stabilization, go-live preparation, and handoff milestones.

# Standard 8-week onboarding sequence

| Week | Milestone | Primary owner | Outputs |
| --- | --- | --- | --- |
| Week 1 | Kickoff and stakeholder alignment | Onboarding manager | Success plan, contact map, cadence, open assumptions log |
| Week 2 | Site and network readiness review | Implementation engineer | Gateway prerequisites, VLAN checklist, warehouse-device inventory |
| Week 3 | Configuration workshop | CSM with customer ops lead | Workflow mapping, role matrix, training roster |
| Week 4 | Pilot data validation | Support engineer | Interface test results, issue list, cutover risks |
| Week 5 | User training and runbook review | Training lead | Completed role-based training, signed runbook |
| Week 6 | Go-live readiness checkpoint | Program lead | Go/no-go assessment, rollback owner list |
| Week 7 | Production cutover | Support lead | Daily war-room updates, open incident list |
| Week 8 | Stabilization and handoff | CSM | Adoption metrics baseline, handoff summary, open-risk register |

# Timeline rules

• The timeline assumes one primary site and no material hardware shortfall. Multi-site programs usually require a staggered plan.

• A week may not be closed until the named milestone outputs are recorded in AtlasCRM or the implementation tracker.

• If training slips by more than five business days, the go-live checkpoint must be re-reviewed rather than silently absorbing the delay.

# Common schedule risks

• Late network approvals, missing customer stakeholder availability, incomplete master data, and delayed device shipments are the most frequent causes of schedule drift.

• When any of these appear, the onboarding manager should open a visible recovery plan rather than continue reporting the original go-live date as if it is still secure.