OrchestrAI Team Knowledge Base

Dependency Risk Register Summary

Condensed risk summary used by PMO to track cross-functional blockers that can delay launches or reduce release readiness.

| Document ID VAL-PROD-004 | Department Product & Program Management | Owner PMO Risk Coordinator | Version 1.0 |
| --- | --- | --- | --- |
| Effective Date 2026-03-24 | Review Cycle Quarterly | Audience PMO, Product, Engineering Leadership, Support, Operations | Classification Internal |

Scope. This summary is not a full portfolio register. It highlights only active risks that affect committed launches, compliance-sensitive work, shared dependencies, or customer enablement timelines.

Active dependency risks

| Risk ID | Description | Severity | Affected launch | Current mitigation | Lead owner |
| --- | --- | --- | --- | --- | --- |
| PR-17 | Warehouse gateway vendor lead time may delay field pilot hardware availability. | Medium | 2026-04-15 edge pilot | Track alternate stock and reserve demo units. | Logistics |
| PR-22 | Security review queue for external API enhancements is longer than plan baseline assumed. | High | Cloud control plane 4.2 | Move review earlier and assign named backup reviewer. | Security |
| PR-24 | Support content for returns workflow has not completed scenario-based macro updates. | Medium | Returns orchestration workflow | Add weekly checkpoint with CS enablement owner. | Customer Success |
| PR-28 | Telemetry event schema is not yet final, which blocks adoption dashboard configuration. | High | Device onboarding UX refresh | Freeze metric definitions before UAT exit. | Product Ops |
| PR-31 | Sales demo environment refresh overlaps with launch training window. | Low | Device onboarding UX refresh | Publish staggered enablement schedule. | Sales Enablement |

Escalation thresholds

High-severity risks with no credible mitigation by the weekly launch review must be escalated to the PMO governance chair.

Any dependency that threatens a customer-announced date requires same-day notification to the owning product manager and revenue lead.

Risks may not be downgraded without evidence that the triggering condition is removed, not merely less visible.

Common retrieval phrases

Useful search cues include dependency risk, affected launch, mitigation owner, portfolio risk register, severity escalation, and weekly launch review.